## ProjectSchedule
HiKiddo - Final Project
Westminster University
Wallyson Alves da Silva
| Project Start: | 2023-09-01
| Display Week: |  |  |  |  | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25 | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15
 | time axis 2023-08-21 to 2024-07-21
Task | Assigned to | Start | Status | End | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1 - Project Proposal and Initialisation
Supervisor Confirmation | WS | 2023-10-05 | Completed | 2023-10-05 | 1
Brain storming about the idea |  | 2023-10-02 | Completed | 2023-10-06
Research Similar Project | WS | 2023-10-06 | Completed | 2023-10-12 | 7
Initial Proposal Completion | WS | 2023-10-13 | Completed | 2023-11-06 | 25
Finalise Proposal and Submission | WS | 2023-11-06 | Completed | 2023-11-09 | 4
Phase 2 - Design and Prototyping Stage
Gather Requirements | WS | 2024-01-10 | Completed | 2024-01-18 | 9
User case Diagram | WS | 2024-01-18 | Completed | 2024-01-21 | 4
Context Diagram | WS | 2024-01-22 | Completed | 2024-01-30 | 9
Firebase Structure Diagram | WS | 2024-02-02 | Completed | 2024-02-05
Wireframe & Story Board | WS | 2024-02-03 | Completed | 2024-02-08 | 6
Prototype | WS | 2024-02-09 | Completed | 2024-02-11 | 3
Documentation for Design Stage | WS | 2024-02-03 | Completed | 2024-02-14 | 12
Phase 3 - Implementation
Create User Login / Sign up | WS | 2024-02-19 | Completed | 2024-02-26 | 8
Create Join Group feature | WS | 2024-02-26 | Completed | 2024-03-04
Create Challenges and Rewards feature | WS | 2024-03-04 | Completed | 2024-03-11
Create Memory Board | WS | 2024-03-11 | Completed | 2024-03-18
Create Voice Recording | WS | 2024-03-18 | Completed | 2024-03-25
Connect application with backend (Firebase) | WS | 2024-02-20 | Completed | 2024-03-25 | 35
Create all methods to add and fetch data from database | WS | 2024-02-21 | Completed | 2024-03-25 | 34
Phase 4 - Testing and Improvement
Create a Test case | WS | 2024-04-04 | on going | 2024-04-23 | 20
Pilot - Unit Testing | WS | 2024-04-04 | Completed | 2024-04-25 | 22
Risk managemet | WS | 2024-04-04 | Completed | 2024-04-25
Mitigation - Improvement based on testing | WS | 2024-04-04 | on going | 2024-04-30
Finalise the project | WS | 2024-04-16 | Completed | 2024-04-30 | 15
Document the testing outcome | WS | 2024-04-16 | Completed | 2024-05-01 | 16
Phase 5 - Depolyment and Documentation
Release Project | WS | TBA |  | TBA
Complete Final Report initial draft | WS | 2023-10-26 |  | 2023-12-02
Finalise Report after feedback | WS | 2023-10-27 |  | 2023-12-03
Phase 6 - Milestones
Formative presentation | WS | 2023-10-24 |  | 2023-10-24 | 1
Proposal submission | WS | 2023-11-09 |  | 2023-11-09
Design and prototype submission | WS | 2023-10-26 |  | 2023-10-26
One-to-one Meeting | WS | 2024-04-24 |  | 2024-04-24
Final year project submission | WS | 2024-05-01 |  | 2024-05-01
VIVA presentation | WS | TBA |  | TBA | #VALUE!